## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Set up environment | 0.5 | 2024-12-10 | Set up the github repository and unity environment
Learning assignment | 2 | 2024-12-10 | Learn about expectations and Maze generation algorithms
https://en.wikipedia.org/wiki/Depth-first_search
https://www.youtube.com/watch?v=Urx87-NMm6c
Set up cell and grid structure | 1 | 2024-12-10 | Implement cells and grid structure the algorithm will use to generate the maze
Implement wall and floor generation | 1 | 2024-12-10 | Added wall and floor prefabs, to be used as presentation of the maze
Implement depth first search algorithm | 3 | 2024-12-10 | Implement the depth first search algorithm, using the concept found on the wiki, and generate walls using the prefabs
Bugfix algorithm | 3 | 2024-12-11 | Had some issues with the wall generation using the algorithm, the walls wouldn’t get removed during the process, resulting in all the cells having 4 walls
Implement UI | 2 | 2024-12-11 | Implement UI and camera, so the user can generate the maze with variable with and length
Implement player | 1.5 | 2024-12-15 | Implemented bonus feature, player character to move trough the maze | x
Implement first person mode | 2 | 2024-12-16 | Implemented bonus feature, first person mode, so the player can walk trough the maze | x
Implement camera switching | 1 | 2024-12-17 | Implement bonus feature, the player can switch from the overview mode to the first person mode | x
Implement camera switching, bugfix | 2 | 2024-12-17 | Had some issues with camera switching and using player prefab, decided to scrap using player prefab for ease of implementation | x
Add aditional comments | 1 | 2024-12-17 | Add comments to make the code understandable
Total amount of hours | 13.5